## PROJECTS IN INDIA
Details of Ongoing Projects having Both Time and Cost Overruns w.r.t Original Schedule
(3RD Quarter,2023-2024)
SI. No. | Sector | Project | Date of Approval | Original Cost (Rs. crore) | Anticipated Cost (Rs.crore) | Original Commissioning Date | Anticipated Commissioning Date | Cost Overruns (%) | Time Over Run (in months)
41 | RAILWAYS | UDHAMPUR-SRINAGAR-BARAMULLA (NL),NR | 1995-03-01 | 2500 | 37012.26 | 2002-11-01 | 2024-02-01 | 1380% | 258.7333
12 | RAILWAYS | KOTLPALLI-NARASAPUR (NL) (SCR) | 2001-12-01 | 1045.2 | 2500.98 | 2009-03-01 | 2027-03-01 | 139.3% | 219.1333
59 | RAILWAYS | KHURDA ROAD-BOLANGIR(NL)ECOR - [220100284 | 1994-04-01 | 2923.13 | 3791.66 | 2009-03-01 | 2026-12-01 | 29.71% | 216.1333
53 | POWER | TAPOVAN-VISHNUGAD HEP (4X130MW) | 2006-11-01 | 2978.48 | 7103 | 2013-03-01 | 2029-04-01 | 138.5% | 195.8333
44 | POWER | PARBATI HEP (4X200 MW) (NHPC) II | 2002-09-01 | 3919.59 | 11063.49 | 2009-09-01 | 2024-09-01 | 182.3% | 182.6333
115 | RAILWAYS | MANOHARABAD-KOTHPALL NEW LINE(SCR) | 2006-04-01 | 1160 | 3014 | 2010-03-01 | 2025-03-01 | 159.8% | 182.6333
1 | POWER | SUBANSIRI LOWER H.E.P (8X250 MW) (NHPC) | 2003-09-01 | 6285.33 | 21247.54 | 2010-09-01 | 2025-05-01 | 238% | 178.5333
57 | ATOMIC ENERGY | PROTOTYPE FAST BREEDER REACTOR (BHAVINI, 500 MWE) | 2003-09-01 | 3492 | 7670 | 2010-09-01 | 2024-12-01 | 119.6% | 173.5
55 | RAILWAYS | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | 2003-04-01 | 4454.17 | 14322 | 2011-03-01 | 2025-03-01 | 221.5% | 170.4667
118 | POWER | VISHNUGAD PIPALKOTI HYDRO ELECTRIC PROJECT | 2008-08-01 | 2491 | 3860.35 | 2013-06-01 | 2026-06-01 | 54.97% | 158.2667
87 | POWER | BARH STPP(3X660MW) NTPC | 2005-02-01 | 8692 | 21312.11 | 2011-10-01 | 2024-08-01 | 145.2% | 156.2667
27 | PETROLEUM | KOCHI-KOOTTANAD-BANGALORE-MANGALORE PIPELINE PHASE-II | 2009-06-01 | 2915 | 5909 | 2012-12-01 | 2024-11-01 | 102.7% | 145.1
90 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM BARANAGAR TO BARRACKPORE AND DAKSHINESHWAR (MTP) | 2010-04-01 | 2298 | 2733.86 | 2014-03-01 | 2025-12-01 | 18.97% | 143.1
109 | RAILWAYS | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT (NEFR) | 2006-04-01 | 2326 | 6663 | 2015-03-01 | 2026-03-01 | 186.5% | 133.9333
23 | RAILWAYS | BHAIRABI SAIRONG, NL, NEFR | 2008-04-01 | 2393.47 | 8605 | 2014-03-01 | 2024-10-01 | 259.5% | 128.9
29 | ROAD TRANSPORT AND HIGHWAYS | VARANASI-AURANGABAD KM.786 TO KM.978.40 | 2011-09-01 | 2848 | 3379.45 | 2014-03-01 | 2024-06-01 | 18.66% | 124.8333
99 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NSCB AIRPORT TO NEW GARIA VIA RAJARHAT (MTP) | 2010-04-01 | 3951 | 8964.35 | 2016-03-01 | 2026-03-01 | 126.9% | 121.7333
19 | ATOMIC ENERGY | RAJASTHAN ATOMIC POWER PROJECT -7 AND 8 (2X700 MW) | 2009-10-01 | 12320 | 17079 | 2016-12-01 | 2026-12-01 | 38.63% | 121.7333
40 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM JOKA TO BINOY BADAL DINESH BAGH. | 2010-04-01 | 2913.51 | 4834.54 | 2016-03-01 | 2025-07-01 | 65.94% | 113.6333
15 | POWER | TEHRI PUMPED STORAGE PLANT(1000MW) | 2006-07-01 | 1657 | 4825.6 | 2016-02-01 | 2024-10-01 | 191.2% | 105.5
4 | ATOMIC ENERGY | KAKRAPAR ATOMIC POWER PROJECT - 3 AND 4 | 2009-10-01 | 11459 | 22517 | 2015-12-01 | 2024-03-01 | 96.5% | 100.4333
16 | PETROLEUM | LIFE EXTENSION OF WALL PLATFORMS OF MUMBAI HIGH AND HEERA FIELDS | 2015-12-01 | 3190.69 | 3375.9 | 2018-04-01 | 2026-05-01 | 5.805% | 98.4
86 | RAILWAYS | SEVOK RANGPO, NEFR | 2008-04-01 | 1339 | 7876.92 | 2015-12-01 | 2023-12-01 | 488.3% | 97.4
60 | RAILWAYS | EAST WEST METRO CORRIDOR FROM HOWRAH MAIDAN TO SALT LAKE | 2013-03-01 | 4874.58 | 10442.41 | 2016-03-01 | 2023-12-01 | 114.2% | 94.3667
84 | RAILWAYS | EAST WEST METRO CORRIDOR KOLKATA | 2009-02-01 | 4874.58 | 10442.41 | 2016-09-01 | 2024-06-01 | 114.2% | 94.3333
62 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF WARANGA-MAHAGAON SECTION(KM253.70 TO 320.580) | 2017-03-01 | 1059.73 | 1071 | 2017-03-01 | 2024-10-01 | 1.063% | 92.3667
76 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF GAYA-HISUA-RAJGIRI-NALANDA- BIHARSHARIF SECTION (KM0.00 TO 92.935) ON NH- 82 IN BIHAR | 2014-01-01 | 1408.85 | 2138.16 | 2016-10-01 | 2024-02-01 | 51.77% | 89.3
8 | ROAD TRANSPORT AND HIGHWAYS | SIX-LANING OF BARWA ADDA-PANAGARH | 2014-04-01 | 1665 | 2360.65 | 2016-09-01 | 2024-01-01 | 41.78% | 89.2667
13 | POWER | RAMMAM-III HEPP (3X40 MW) | 2014-09-01 | 1381.84 | 1803 | 2019-09-01 | 2026-12-01 | 30.48% | 88.2667
97 | ROAD TRANSPORT AND HIGHWAYS | HOSPET-BELLARY-KARNATAKA AP BORDER | 2016-08-01 | 1167 | 1224.01 | 2019-03-01 | 2025-05-01 | 4.885% | 75.1
61 | POWER | COMPREHENSIVE SCHEME FOR THE STRENGHTENING OF THE TRANSMISSION AND DISTRIBUTION SYSTEM IN A P | 2014-12-01 | 4754.42 | 9129.32 | 2018-12-01 | 2024-12-01 | 92.02% | 73.0667
73 | POWER | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT (NERPSIP) FOR SIX (6) STATES | 2014-12-01 | 5111.33 | 6700 | 2018-12-01 | 2024-12-01 | 31.08% | 73.0667
14 | RAILWAYS | HOTGI-KUDGI-GADAG | 2015-03-01 | 1614.59 | 1960 | 2019-03-01 | 2024-12-01 | 21.39% | 70.0667
22 | PETROLEUM | KOCHI SALEM LPG PIPELINE PROJECT | 2015-12-01 | 1112 | 1507.24 | 2019-06-01 | 2025-02-01 | 35.54% | 69.0667
79 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF SULTANPUR TO VARANASI (PKG- I) | 2016-01-01 | 1027.53 | 2628.31 | 2018-06-01 | 2023-12-01 | 155.8% | 66.9667
78 | PETROLEUM | ENNORE THIRUVALLUR BENGALURU PUDUCHERRY NAGAPATTINAM MADURAITUTICORIN GAS PIPELINE | 2016-05-01 | 4497 | 6025 | 2018-12-01 | 2024-03-01 | 33.98% | 63.9
70 | RAILWAYS | KHARSIA DHARAMJAIGARH WITH SPUR LINE EAST CORRIDOR-PHASE I | 2013-04-01 | 3055 | 3438.39 | 2018-09-01 | 2023-12-01 | 12.55% | 63.9
11 | COAL | RANIGANJ MASTER PLAN | 2009-08-01 | 2661.73 | 5146.48 | 2019-08-01 | 2024-08-01 | 93.35% | 60.9
103 | RAILWAYS | TARAKESWAR - BISHNUPUR NEW BG LINE (NL) | 2000-04-01 | 1188 | 1619.51 | 2019-03-01 | 2024-03-01 | 36.32% | 60.9
56 | POWER | NORTH KARANPURA STPP (3X660 MW) | 2014-02-01 | 14366.58 | 17007 | 2019-06-01 | 2024-06-01 | 18.38% | 60.9
75 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF VARANASI GORAKHPUR SECTION OF NH-29 FROM 148.00 208.300 KM [PACKAGE-IV] | 2016-03-01 | 1587.49 | 3063.99 | 2019-04-01 | 2024-03-01 | 93.01% | 59.8667
67 | RAILWAYS | NEW BONGAIGAON-RANGIA-KAMAKGHYA DOUBLING | 2013-04-01 | 1798 | 2047.51 | 2019-03-01 | 2024-01-01 | 13.88% | 58.9
2 | RAILWAYS | AHMEDNAGAR-PARLI VAIJNATH(NL) CR | 1997-02-01 | 2271.5 | 4805.17 | 2021-03-01 | 2025-12-01 | 111.5% | 57.8667
102 | RAILWAYS | CHOTTAUDEPUR-DHAR(NL) | 2007-04-01 | 1347 | 1793.63 | 2022-03-01 | 2026-12-01 | 33.16% | 57.8667
34 | RAILWAYS | KATNI - SINGRAULI DOUBLING PROJECT | 2015-12-01 | 1763.93 | 2445.3 | 2020-03-01 | 2024-10-01 | 38.63% | 55.8333
37 | MINES | 5TH STREAM ALUMINA REFINERY EXPANSION PROJECT - | 2014-12-01 | 4103 | 5677.4 | 2021-04-01 | 2025-09-01 | 38.37% | 53.8
46 | ROAD TRANSPORT AND HIGHWAYS | BONDAMUNDA RANCHI DOUBLING | 2016-03-01 | 1724.2 | 3029.04 | 2021-03-01 | 2025-06-01 | 75.68% | 51.7667
45 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF SATTANATHAPURAM (KM.123/800) TO NAGAPATTINAM (KM.179/555) SECTION OF NH- 45A ON HAM UN | 2018-03-01 | 1872.68 | 2756.09 | 2020-10-01 | 2025-01-01 | 47.17% | 51.7667
68 | RAILWAYS | SHAHGANJ-BHATNI-PHEPHNA-INDARA, MAU- SHAHGANJ (EXCL. MAU-INDARA) PATCH DOUBLING. | 2016-04-01 | 1177.96 | 1777.39 | 2019-12-01 | 2024-03-01 | 50.89% | 51.7333
26 | POWER | HVDC BIPOLE LINK BETWEEN WR AND SR -NORTH TRICHUR - SCHEME -II AC SYSTEM STRENGTHENING AT PUGALUR EN | 2017-08-01 | 1931.39 | 2635.55 | 2020-02-01 | 2024-03-01 | 36.46% | 49.6667
38 | WATER RESOURCES | POLAVARAM IRRIGATION PROJECT | 2009-02-01 | 10151.04 | 55548.87 | 2020-03-01 | 2024-03-01 | 447.2% | 48.7
71 | RAILWAYS | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | 2015-04-01 | 2232.32 | 4059.65 | 2022-03-01 | 2026-03-01 | 81.86% | 48.7
94 | RAILWAYS | RATLAM-MHOW-KHANDWA-AKOLA (GC) | 2008-04-01 | 3503 | 6203.51 | 2022-03-01 | 2026-03-01 | 77.09% | 48.7
112 | RAILWAYS | DAHOD-INDORE VIA SARDARPUR, JHABUA AND DHAR (NL) | 2007-04-01 | 1640 | 2690.8 | 2022-03-01 | 2026-03-01 | 64.07% | 48.7
42 | RAILWAYS | KIRANDUL - JAGDALPUR DOUBLING | 2012-12-01 | 1160 | 1440 | 2020-03-01 | 2024-03-01 | 24.14% | 48.7
117 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BAKHTIYARPUR - MOKAMA SECTION OF NH-31 | 2015-12-01 | 1167 | 1182.94 | 2019-12-01 | 2023-12-01 | 1.366% | 48.7
108 | RAILWAYS | KAZIPET-BALHRSHA | 2015-04-01 | 2063 | 2909 | 2021-03-01 | 2025-01-01 | 41.01% | 46.7333
120 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF HARIDWAR-NAGINA SECTION OF NH 74 FROM (KM 204.300 OF NH 58) TO KM 73.00 | 2016-03-01 | 1408 | 1659.12 | 2020-07-01 | 2024-05-01 | 17.84% | 46.6667
43 | RAILWAYS | WARDHA-NANDED MAHARASHTRA | 2008-04-01 | 3168.29 | 3445.48 | 2023-03-01 | 2026-12-01 | 8.749% | 45.7
66 | URBAN DEVELOPMENT | MUMBAI METRO LINE 3 (COLABA-BANDRA-SEEPZ) | 2013-07-01 | 23136 | 37276 | 2020-03-01 | 2023-12-01 | 61.12% | 45.6667
88 | PETROLEUM | VISAKH REFINERY MODERNISATION PROJECT | 2016-07-01 | 20928 | 26264 | 2020-07-01 | 2024-04-01 | 25.5% | 45.6667
82 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF THALSERRY -MAHE BYPASS | 2017-09-01 | 1124.11 | 1503.86 | 2020-05-01 | 2024-01-01 | 33.78% | 44.6667
106 | RAILWAYS | JHARSUGUDA-BILASPUR 4TH LINE | 2015-04-01 | 1973 | 2135.34 | 2021-03-01 | 2024-10-01 | 8.228% | 43.6667
69 | PETROLEUM | DURGAPUR-HALDIA PIPELINE PROJECT | 2017-03-01 | 1740 | 2433.15 | 2020-12-01 | 2024-06-01 | 39.84% | 42.6
32 | CIVIL AVIATION | CCS INTERNATIONAL AIRPORT , LUCKNOW | 2018-06-01 | 1383 | 3291.81 | 2021-09-01 | 2024-12-01 | 138% | 39.5667
116 | ROAD TRANSPORT AND HIGHWAYS | SIX LANNING FROM KM. 401.200 TO 494.410 OF NH-8 ON HYBRID ANNUITY MODE UNDER NHDP-V(PKG VI)REG. | 2017-01-01 | 1251 | 1361 | 2020-12-01 | 2024-03-01 | 8.793% | 39.5333
9 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF 8 LANING OF EXISTING 4 LANE VADAPE TO THANE FROM KM 539.202 TO KM 563.000 SECTION OF | 2018-03-01 | 1162.92 | 1182.87 | 2021-07-01 | 2024-09-01 | 1.716% | 38.6
31 | POWER | TELANGANA SUPER THERMAL POWER PROJECT PHASE I - | 2016-01-01 | 10598.98 | 10998 | 2020-11-01 | 2024-01-01 | 3.765% | 38.5333
113 | ROAD TRANSPORT AND HIGHWAYS | 6-LANING OF VIJAYAWADA BYPASS FROM CHINNA AVUTUPALLI (DESIGN CH.0+000) TO GOLLAPUDI | 2019-11-01 | 1226 | 1581.24 | 2021-02-01 | 2024-03-01 | 28.98% | 37.4667
105 | RAILWAYS | ANUPPUR-KATNI | 2015-04-01 | 1370 | 1680 | 2021-12-01 | 2024-12-01 | 22.63% | 36.5333
33 | RAILWAYS | WARDHA-BALHARSHAH - 3RD LINE (132 KM) | 2015-02-01 | 1272.19 | 1384.72 | 2022-03-01 | 2025-03-01 | 8.845% | 36.5333
101 |  | 4-LANING OF LOHA - WARANGA SECTION OF NH- 361 FROM KM. 187.800 TO KM. 244.369 (DESIGN LENGTH 56.569 K | 2018-03-01 | 1005 | 1073.1 | 2021-03-01 | 2024-03-01 | 6.776% | 36.5333
52 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE VADODARA KIM EXPRESSWAY FROM KM 254.430 TO KM 279.000 (KIM TO ANKLESHWAR | 2018-03-01 | 1161.39 | 1404 | 2021-10-01 | 2024-09-01 | 20.89% | 35.5333
10 | COAL | NEYVELI UTTAR PRADESH POWER PROJECT LIMITED 1980 MW - | 2016-07-01 | 17237 | 19406.12 | 2021-11-01 | 2024-10-01 | 12.58% | 35.5
18 | RAILWAYS | GWALIOR-SEOPURKALA WITH EXTENSION TO KOTA (GC) | 2011-04-01 | 2912.96 | 3845.6 | 2022-03-01 | 2024-12-01 | 32.02% | 33.5333
81 | ROAD TRANSPORT AND HIGHWAYS | 4L OF AUSA-CHAKUR SECTION FROM KM 55.835 TO KM 114.345 OF NH-361 | 2018-03-01 | 1169.04 | 1693.95 | 2021-03-01 | 2023-12-01 | 44.9% | 33.5
49 | PETROLEUM | R and D CAMPUS II AT FARIDABAD | 2019-06-01 | 2281.94 | 3219.94 | 2022-12-01 | 2025-07-01 | 41.11% | 31.4333
74 | ROAD TRANSPORT AND HIGHWAYS | 8L OF DWARKA EXPRESSWAY PKG-II (RUB NEAR DWARKA SECTOR 21-DL/HR BORDER) FROM 5.300 KM.TO 9.500 KM. O | 2018-01-01 | 2067.67 | 2160 | 2021-10-01 | 2024-04-01 | 4.465% | 30.4333
65 | ROAD TRANSPORT AND HIGHWAYS | SIX LANING OF CHAKERI TO ALLAHABAD SECTION OF NH-2 FROM KM 483.687 TO KM 628.753 (DESIGN LENGTH – 14 | 2017-11-01 | 2159 | 2262 | 2021-07-01 | 2023-12-01 | 4.771% | 29.4333
36 | PETROLEUM | RAJASTHAN REFINERY PROJECT | 2017-10-01 | 43129 | 72937 | 2022-10-01 | 2025-03-01 | 69.11% | 29.4
72 | URBAN DEVELOPMENT | PUNE METRO RAIL PROJECT (PHASE 1) | 2016-12-01 | 11420 | 13656.22 | 2021-11-01 | 2024-03-01 | 19.58% | 28.3667
93 | PETROLEUM | MUMBAI HIGH NORTH REDEVELOPMENT PHASE-IV | 2019-04-01 | 3228 | 3976.67 | 2022-03-01 | 2024-06-01 | 23.19% | 27.4333
3 | RAILWAYS | KATNI-BINA 3RD LINE (263 KM) | 2016-06-01 | 2478.23 | 2938 | 2022-03-01 | 2024-06-01 | 18.55% | 27.4333
21 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF KARADI TO BANAVARA SECTION FROM KM. 66+540 (DESIGN KM. 65+195) TO KM.119+790 (DESIGN | 2019-10-01 | 1225.24 | 1505.85 | 2021-10-01 | 2024-01-01 | 22.9% | 27.4
98 | RAILWAYS | KAZIPET-VIJAYAWADA 3RD LINE WITH ELECTRIFICATION | 2012-04-01 | 1856 | 1952.68 | 2023-03-01 | 2025-03-01 | 5.209% | 24.3667
58 | RAILWAYS | MANIYACHI - NAGERCOIL (102 KM) DOUBLING | 2015-02-01 | 1700 | 1752.25 | 2022-03-01 | 2024-03-01 | 3.074% | 24.3667
7 | RAILWAYS | VIZIANAGARAM -SAMABALPUR 3RD LINE | 1991-01-01 | 2335.67 | 4803.16 | 2024-12-01 | 2026-12-01 | 105.6% | 24.3333
20 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANÌNG OF PUDUCHERRY (KM.29/000) TO POONDIYANKUPPAM (KM.67/000) SECTION OF NH- 45A ON HAM UNDER | 2018-03-01 | 1294.47 | 1588.4 | 2021-11-01 | 2023-11-01 | 22.71% | 24.3333
77 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF POONDIYANKUPPAM (KM.67/000) TO SATTANATHAPOURAM (KM.123/800) SECTION OF NH-45A ON HAM | 2018-03-01 | 2120.4 | 2565.63 | 2022-01-01 | 2024-01-01 | 21% | 24.3333
85 | RAILWAYS | ROSA-SITAPUR CANTT-BURHWAL DOUBLING | 2015-03-01 | 1295 | 2560 | 2022-03-01 | 2024-02-01 | 97.68% | 23.4
50 | PETROLEUM | KOYALI AHMEDNAGAR SOLAPUR PIPELINE | 2016-05-01 | 1945 | 2251 | 2022-02-01 | 2024-01-01 | 15.73% | 23.3
96 | ROAD TRANSPORT AND HIGHWAYS | 6-LANING OF KOZHIKODE BYPASS (CALICUT BYPASS) (I.E. VENGALAM JN. TO RAMANATTUKARA JN.) | 2018-02-01 | 1424 | 1862.77 | 2023-02-01 | 2024-12-01 | 30.81% | 22.3
39 | RAILWAYS | RAJNANDGAON - NAGPUR - 3RD LINE (SECR) | 2016-09-01 | 1908.51 | 3544.25 | 2023-03-01 | 2024-12-01 | 85.71% | 21.3667
24 | RAILWAYS | DAUND - MANMAD (236 KM) | 2016-02-01 | 1876 | 2081.27 | 2023-03-01 | 2024-12-01 | 10.94% | 21.3667
111 | ROAD TRANSPORT AND HIGHWAYS | DWARKA EXPRESSWAY FROM KM -0.600 TO KM 5.300 - PKG-I (SHIVMURTI CHOWK-RUB NEAR DWARKA SECTOR 21) | 2018-03-01 | 2507 | 3030.73 | 2022-09-01 | 2024-06-01 | 20.89% | 21.3
5 | PETROLEUM | CAPACITY EXPANSION OF PANIPAT REFINERY FROM 15 TO 25 MMTPA - [N16000412 | 2021-02-01 | 34627 | 38231 | 2024-09-01 | 2025-12-01 | 10.41% | 15.2
6 | STEEL | SCREENING PLANT-III AT KIRANDUL | 2021-03-01 | 2092.97 | 2718.84 | 2024-08-01 | 2025-10-01 | 29.9% | 14.2
47 | ROAD TRANSPORT AND HIGHWAYS | 6L OF AZHIYUR-VENGALAM FROM KM. 189.200 TO KM. 230.400 OF NH-66 | 2020-10-01 | 3219.47 | 3713.14 | 2024-04-01 | 2025-05-01 | 15.33% | 13.1667
104 | RAILWAYS | HOSPET-HUBLI-LONDA-VASCODAGAMA DL | 2010-04-01 | 2127 | 3692.6 | 2023-03-01 | 2024-03-01 | 73.61% | 12.2
100 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BETTADAHALLI TO SRIRAMPURA SECTION FROM KM. 166+100 (DESIGN KM. 170+415) TO KM. 217+0 | 2021-10-01 | 1331 | 2082.98 | 2023-10-01 | 2024-10-01 | 56.5% | 12.2
51 | ROAD TRANSPORT AND HIGHWAYS | 4 LANING FROM KM. 34.600 TO KM. 79.970 and 2LPS FROM KM. 79.970 TO KM. 82.000 OF NARENPUR - PURNEA S | 2020-09-01 | 2334.68 | 2335 | 2023-03-01 | 2024-02-01 | 0.01371% | 11.2333
95 | ROAD TRANSPORT AND HIGHWAYS | LUCKNOW RING ROAD PKG-1 (SULTANPUR ROAD TO BEHTA ROAD) [BYPASS CONNECTING NH-56 AT KM. 17.40 | 2018-01-01 | 1916.38 | 2078 | 2023-02-01 | 2024-01-01 | 8.434% | 11.1333
114 | ROAD TRANSPORT AND HIGHWAYS | CHAKUR LOHA SECTION OF NH-361 FROM KM 114.600 TO KM 187.80 | 2018-03-01 | 1241 | 2122.64 | 2023-03-01 | 2024-01-01 | 71.04% | 10.2
48 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BANAVARA TO BETTADAHALLI SECTION FROM KM. 119+790 (DESIGN KM. 121+900) TO KM. 166+100 | 2021-03-01 | 1065.06 | 1444.5 | 2023-03-01 | 2024-01-01 | 35.63% | 10.2
80 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE EXPRESSWAY FROM KM 190.000 TO KM 217.500 GANDEVA TO ENA SECTION OF VADODA | 2020-07-01 | 1710.3 | 1927 | 2023-08-01 | 2024-06-01 | 12.67% | 10.1667
25 | PETROLEUM | ACRYLICS OR OXO-ALCOHOL PROJECT AT GUJARAT REFINERY - | 2019-11-01 | 5251 | 5894 | 2023-05-01 | 2024-03-01 | 12.25% | 10.1667
54 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BAL. WORKS OF BARASAT- KRISHNAGAR FROM KM.48.553 TO KM.115.272 | 2018-12-01 | 2375.87 | 2566.8 | 2023-02-01 | 2023-12-01 | 8.036% | 10.1
64 | RAILWAYS | PUNE-MIRAJ-LONDA (467 KM) | 2015-02-01 | 3627.47 | 6463.49 | 2024-03-01 | 2024-12-01 | 78.18% | 9.1667
35 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 103.400 TO KM 128.000 OF VADODARA MU | 2021-03-01 | 1259 | 1910 | 2024-03-01 | 2024-12-01 | 51.71% | 9.1667
30 | POWER | NORTH EAST-NORTHERN/ WESTERN INTERCONNECTOR-I, PART-C | 2019-03-01 | 1326 | 1520 | 2023-03-01 | 2023-12-01 | 14.63% | 9.1667
89 | PETROLEUM | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | 2019-01-01 | 12366 | 18968 | 2024-10-01 | 2025-07-01 | 53.39% | 9.1
28 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF MAMALLAPURAM TO MUGAIYUR SECTION OF NH332A FROM KM 0.000 TO KM 31.000 | 2019-02-01 | 1008.99 | 1361 | 2024-05-01 | 2024-11-01 | 34.89% | 6.1333
91 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 217.500 TO KM 254.430 OF VADODARA | 2020-07-01 | 2271 | 3916 | 2023-12-01 | 2024-06-01 | 72.44% | 6.1
83 | PETROLEUM | SETTING UP 500KTPA PROPANE DEHYDROGENATION INTEGRATED WITH POLYPROPYLENE UNIT ALONG WITH OFFSITE | 2019-05-01 | 8797 | 11256 | 2025-04-01 | 2025-10-01 | 27.95% | 6.1
63 | ROAD TRANSPORT AND HIGHWAYS | 4L OF NAGPUR-KATOL SECTION FROM KM. 13.00 TO KM. 62.900 OF NH-353J | 2021-02-01 | 1166.96 | 1251 | 2023-10-01 | 2024-04-01 | 7.202% | 6.1
107 | URBAN DEVELOPMENT | PATNA METRO RAIL CORPORATION LIMITED | 2019-02-01 | 13365 | 13925.5 | 2024-06-01 | 2024-09-01 | 4.194% | 3.0667
119 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF 4-LANE GREEN FIELD DELHI- AMRITSAR-KATRA EXPRESSWAY (NE-05) FROM JUSSUR KHERI ON KMP | 2020-11-01 | 1690 | 2010.17 | 2023-12-01 | 2024-03-01 | 18.94% | 3.0333
110 | RAILWAYS | RISHIKESH - KARNAPRAYAG NEW LINE | 2011-04-01 | 16216 | 24659 | 2024-12-01 | 2025-03-01 | 52.07% | 3
17 | PETROLEUM | SETTING UP LUBE COMPLEX AT VILLAGES AMULLAVOYAL AND VAIKKADU, CHENNAI AS RESITEMENT OF EXISTING FACI | 2020-10-01 | 1398 | 1587 | 2023-12-01 | 2024-02-01 | 13.52% | 2.0667
92 | ROAD TRANSPORT AND HIGHWAYS | ALIGARH-KANPUR SECTION PACKAGEV FROM MITRASEN-KANPUR | 2019-10-01 | 2325 | 3601.57 | 2023-09-01 | 2023-10-01 | 54.91% | 1

## Sheet1
SI. No. | Sector | Project | Date of Approval | Original Cost (Rs. crore) | Anticipated Cost (Rs.crore) | Original Commissioning Date | Anticipated Commissioning Date | Cost Overruns (%) | Time Over Run (in months)
1 | POWER | SUBANSIRI LOWER H.E.P (8X250 MW) (NHPC) | 2003-09-01 | 6285.33 | 21247.54 | 2010-09-01 | 2025-05-01 | 238% | 178.5333
2 | RAILWAYS | AHMEDNAGAR-PARLI VAIJNATH(NL) CR | 1997-02-01 | 2271.5 | 4805.17 | 2021-03-01 | 2025-12-01 | 111.5% | 57.8667
3 | RAILWAYS | KATNI-BINA 3RD LINE (263 KM) | 2016-06-01 | 2478.23 | 2938 | 2022-03-01 | 2024-06-01 | 18.55% | 27.4333
4 | ATOMIC ENERGY | KAKRAPAR ATOMIC POWER PROJECT - 3 AND 4 | 2009-10-01 | 11459 | 22517 | 2015-12-01 | 2024-03-01 | 96.5% | 100.4333
5 | PETROLEUM | CAPACITY EXPANSION OF PANIPAT REFINERY FROM 15 TO 25 MMTPA - [N16000412 | 2021-02-01 | 34627 | 38231 | 2024-09-01 | 2025-12-01 | 10.41% | 15.2
6 | STEEL | SCREENING PLANT-III AT KIRANDUL | 2021-03-01 | 2092.97 | 2718.84 | 2024-08-01 | 2025-10-01 | 29.9% | 14.2
7 | RAILWAYS | VIZIANAGARAM -SAMABALPUR 3RD LINE | 1991-01-01 | 2335.67 | 4803.16 | 2024-12-01 | 2026-12-01 | 105.6% | 24.3333
8 | ROAD TRANSPORT AND HIGHWAYS | SIX-LANING OF BARWA ADDA-PANAGARH | 2014-04-01 | 1665 | 2360.65 | 2016-09-01 | 2024-01-01 | 41.78% | 89.2667
9 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF 8 LANING OF EXISTING 4 LANE VADAPE TO THANE FROM KM 539.202 TO KM 563.000 SECTION OF | 2018-03-01 | 1162.92 | 1182.87 | 2021-07-01 | 2024-09-01 | 1.716% | 38.6
10 | COAL | NEYVELI UTTAR PRADESH POWER PROJECT LIMITED 1980 MW - | 2016-07-01 | 17237 | 19406.12 | 2021-11-01 | 2024-10-01 | 12.58% | 35.5
11 | COAL | RANIGANJ MASTER PLAN | 2009-08-01 | 2661.73 | 5146.48 | 2019-08-01 | 2024-08-01 | 93.35% | 60.9
12 | RAILWAYS | KOTLPALLI-NARASAPUR (NL) (SCR) | 2001-12-01 | 1045.2 | 2500.98 | 2009-03-01 | 2027-03-01 | 139.3% | 219.1333
13 | POWER | RAMMAM-III HEPP (3X40 MW) | 2014-09-01 | 1381.84 | 1803 | 2019-09-01 | 2026-12-01 | 30.48% | 88.2667
14 | RAILWAYS | HOTGI-KUDGI-GADAG | 2015-03-01 | 1614.59 | 1960 | 2019-03-01 | 2024-12-01 | 21.39% | 70.0667
15 | POWER | TEHRI PUMPED STORAGE PLANT(1000MW) | 2006-07-01 | 1657 | 4825.6 | 2016-02-01 | 2024-10-01 | 191.2% | 105.5
16 | PETROLEUM | LIFE EXTENSION OF WALL PLATFORMS OF MUMBAI HIGH AND HEERA FIELDS | 2015-12-01 | 3190.69 | 3375.9 | 2018-04-01 | 2026-05-01 | 5.805% | 98.4
17 | PETROLEUM | SETTING UP LUBE COMPLEX AT VILLAGES AMULLAVOYAL AND VAIKKADU, CHENNAI AS RESITEMENT OF EXISTING FACI | 2020-10-01 | 1398 | 1587 | 2023-12-01 | 2024-02-01 | 13.52% | 2.0667
18 | RAILWAYS | GWALIOR-SEOPURKALA WITH EXTENSION TO KOTA (GC) | 2011-04-01 | 2912.96 | 3845.6 | 2022-03-01 | 2024-12-01 | 32.02% | 33.5333
19 | ATOMIC ENERGY | RAJASTHAN ATOMIC POWER PROJECT -7 AND 8 (2X700 MW) | 2009-10-01 | 12320 | 17079 | 2016-12-01 | 2026-12-01 | 38.63% | 121.7333
20 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANÌNG OF PUDUCHERRY (KM.29/000) TO POONDIYANKUPPAM (KM.67/000) SECTION OF NH- 45A ON HAM UNDER | 2018-03-01 | 1294.47 | 1588.4 | 2021-11-01 | 2023-11-01 | 22.71% | 24.3333
21 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF KARADI TO BANAVARA SECTION FROM KM. 66+540 (DESIGN KM. 65+195) TO KM.119+790 (DESIGN | 2019-10-01 | 1225.24 | 1505.85 | 2021-10-01 | 2024-01-01 | 22.9% | 27.4
22 | PETROLEUM | KOCHI SALEM LPG PIPELINE PROJECT | 2015-12-01 | 1112 | 1507.24 | 2019-06-01 | 2025-02-01 | 35.54% | 69.0667
23 | RAILWAYS | BHAIRABI SAIRONG, NL, NEFR | 2008-04-01 | 2393.47 | 8605 | 2014-03-01 | 2024-10-01 | 259.5% | 128.9
24 | RAILWAYS | DAUND - MANMAD (236 KM) | 2016-02-01 | 1876 | 2081.27 | 2023-03-01 | 2024-12-01 | 10.94% | 21.3667
25 | PETROLEUM | ACRYLICS OR OXO-ALCOHOL PROJECT AT GUJARAT REFINERY - | 2019-11-01 | 5251 | 5894 | 2023-05-01 | 2024-03-01 | 12.25% | 10.1667
26 | POWER | HVDC BIPOLE LINK BETWEEN WR AND SR -NORTH TRICHUR - SCHEME -II AC SYSTEM STRENGTHENING AT PUGALUR EN | 2017-08-01 | 1931.39 | 2635.55 | 2020-02-01 | 2024-03-01 | 36.46% | 49.6667
27 | PETROLEUM | KOCHI-KOOTTANAD-BANGALORE-MANGALORE PIPELINE PHASE-II | 2009-06-01 | 2915 | 5909 | 2012-12-01 | 2024-11-01 | 102.7% | 145.1
28 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF MAMALLAPURAM TO MUGAIYUR SECTION OF NH332A FROM KM 0.000 TO KM 31.000 | 2019-02-01 | 1008.99 | 1361 | 2024-05-01 | 2024-11-01 | 34.89% | 6.1333
29 | ROAD TRANSPORT AND HIGHWAYS | VARANASI-AURANGABAD KM.786 TO KM.978.40 | 2011-09-01 | 2848 | 3379.45 | 2014-03-01 | 2024-06-01 | 18.66% | 124.8333
30 | POWER | NORTH EAST-NORTHERN/ WESTERN INTERCONNECTOR-I, PART-C | 2019-03-01 | 1326 | 1520 | 2023-03-01 | 2023-12-01 | 14.63% | 9.1667
31 | POWER | TELANGANA SUPER THERMAL POWER PROJECT PHASE I - | 2016-01-01 | 10598.98 | 10998 | 2020-11-01 | 2024-01-01 | 3.765% | 38.5333
32 | CIVIL AVIATION | CCS INTERNATIONAL AIRPORT , LUCKNOW | 2018-06-01 | 1383 | 3291.81 | 2021-09-01 | 2024-12-01 | 138% | 39.5667
33 | RAILWAYS | WARDHA-BALHARSHAH - 3RD LINE (132 KM) | 2015-02-01 | 1272.19 | 1384.72 | 2022-03-01 | 2025-03-01 | 8.845% | 36.5333
34 | RAILWAYS | KATNI - SINGRAULI DOUBLING PROJECT | 2015-12-01 | 1763.93 | 2445.3 | 2020-03-01 | 2024-10-01 | 38.63% | 55.8333
35 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 103.400 TO KM 128.000 OF VADODARA MU | 2021-03-01 | 1259 | 1910 | 2024-03-01 | 2024-12-01 | 51.71% | 9.1667
36 | PETROLEUM | RAJASTHAN REFINERY PROJECT | 2017-10-01 | 43129 | 72937 | 2022-10-01 | 2025-03-01 | 69.11% | 29.4
37 | MINES | 5TH STREAM ALUMINA REFINERY EXPANSION PROJECT - | 2014-12-01 | 4103 | 5677.4 | 2021-04-01 | 2025-09-01 | 38.37% | 53.8
38 | WATER RESOURCES | POLAVARAM IRRIGATION PROJECT | 2009-02-01 | 10151.04 | 55548.87 | 2020-03-01 | 2024-03-01 | 447.2% | 48.7
39 | RAILWAYS | RAJNANDGAON - NAGPUR - 3RD LINE (SECR) | 2016-09-01 | 1908.51 | 3544.25 | 2023-03-01 | 2024-12-01 | 85.71% | 21.3667
40 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM JOKA TO BINOY BADAL DINESH BAGH. | 2010-04-01 | 2913.51 | 4834.54 | 2016-03-01 | 2025-07-01 | 65.94% | 113.6333
41 | RAILWAYS | UDHAMPUR-SRINAGAR-BARAMULLA (NL),NR | 1995-03-01 | 2500 | 37012.26 | 2002-11-01 | 2024-02-01 | 1380% | 258.7333
42 | RAILWAYS | KIRANDUL - JAGDALPUR DOUBLING | 2012-12-01 | 1160 | 1440 | 2020-03-01 | 2024-03-01 | 24.14% | 48.7
43 | RAILWAYS | WARDHA-NANDED MAHARASHTRA | 2008-04-01 | 3168.29 | 3445.48 | 2023-03-01 | 2026-12-01 | 8.749% | 45.7
44 | POWER | PARBATI HEP (4X200 MW) (NHPC) II | 2002-09-01 | 3919.59 | 11063.49 | 2009-09-01 | 2024-09-01 | 182.3% | 182.6333
45 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF SATTANATHAPURAM (KM.123/800) TO NAGAPATTINAM (KM.179/555) SECTION OF NH- 45A ON HAM UN | 2018-03-01 | 1872.68 | 2756.09 | 2020-10-01 | 2025-01-01 | 47.17% | 51.7667
46 | ROAD TRANSPORT AND HIGHWAYS | BONDAMUNDA RANCHI DOUBLING | 2016-03-01 | 1724.2 | 3029.04 | 2021-03-01 | 2025-06-01 | 75.68% | 51.7667
47 | ROAD TRANSPORT AND HIGHWAYS | 6L OF AZHIYUR-VENGALAM FROM KM. 189.200 TO KM. 230.400 OF NH-66 | 2020-10-01 | 3219.47 | 3713.14 | 2024-04-01 | 2025-05-01 | 15.33% | 13.1667
48 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BANAVARA TO BETTADAHALLI SECTION FROM KM. 119+790 (DESIGN KM. 121+900) TO KM. 166+100 | 2021-03-01 | 1065.06 | 1444.5 | 2023-03-01 | 2024-01-01 | 35.63% | 10.2
49 | PETROLEUM | R and D CAMPUS II AT FARIDABAD | 2019-06-01 | 2281.94 | 3219.94 | 2022-12-01 | 2025-07-01 | 41.11% | 31.4333
50 | PETROLEUM | KOYALI AHMEDNAGAR SOLAPUR PIPELINE | 2016-05-01 | 1945 | 2251 | 2022-02-01 | 2024-01-01 | 15.73% | 23.3
51 | ROAD TRANSPORT AND HIGHWAYS | 4 LANING FROM KM. 34.600 TO KM. 79.970 and 2LPS FROM KM. 79.970 TO KM. 82.000 OF NARENPUR - PURNEA S | 2020-09-01 | 2334.68 | 2335 | 2023-03-01 | 2024-02-01 | 0.01371% | 11.2333
52 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE VADODARA KIM EXPRESSWAY FROM KM 254.430 TO KM 279.000 (KIM TO ANKLESHWAR | 2018-03-01 | 1161.39 | 1404 | 2021-10-01 | 2024-09-01 | 20.89% | 35.5333
53 | POWER | TAPOVAN-VISHNUGAD HEP (4X130MW) | 2006-11-01 | 2978.48 | 7103 | 2013-03-01 | 2029-04-01 | 138.5% | 195.8333
54 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BAL. WORKS OF BARASAT- KRISHNAGAR FROM KM.48.553 TO KM.115.272 | 2018-12-01 | 2375.87 | 2566.8 | 2023-02-01 | 2023-12-01 | 8.036% | 10.1
55 | RAILWAYS | JIRIBAM TO IMPHAL (TUPUI)(NL)(NEFR) | 2003-04-01 | 4454.17 | 14322 | 2011-03-01 | 2025-03-01 | 221.5% | 170.4667
56 | POWER | NORTH KARANPURA STPP (3X660 MW) | 2014-02-01 | 14366.58 | 17007 | 2019-06-01 | 2024-06-01 | 18.38% | 60.9
57 | ATOMIC ENERGY | PROTOTYPE FAST BREEDER REACTOR (BHAVINI, 500 MWE) | 2003-09-01 | 3492 | 7670 | 2010-09-01 | 2024-12-01 | 119.6% | 173.5
58 | RAILWAYS | MANIYACHI - NAGERCOIL (102 KM) DOUBLING | 2015-02-01 | 1700 | 1752.25 | 2022-03-01 | 2024-03-01 | 3.074% | 24.3667
59 | RAILWAYS | KHURDA ROAD-BOLANGIR(NL)ECOR - [220100284 | 1994-04-01 | 2923.13 | 3791.66 | 2009-03-01 | 2026-12-01 | 29.71% | 216.1333
60 | RAILWAYS | EAST WEST METRO CORRIDOR FROM HOWRAH MAIDAN TO SALT LAKE | 2013-03-01 | 4874.58 | 10442.41 | 2016-03-01 | 2023-12-01 | 114.2% | 94.3667
61 | POWER | COMPREHENSIVE SCHEME FOR THE STRENGHTENING OF THE TRANSMISSION AND DISTRIBUTION SYSTEM IN A P | 2014-12-01 | 4754.42 | 9129.32 | 2018-12-01 | 2024-12-01 | 92.02% | 73.0667
62 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF WARANGA-MAHAGAON SECTION(KM253.70 TO 320.580) | 2017-03-01 | 1059.73 | 1071 | 2017-03-01 | 2024-10-01 | 1.063% | 92.3667
63 | ROAD TRANSPORT AND HIGHWAYS | 4L OF NAGPUR-KATOL SECTION FROM KM. 13.00 TO KM. 62.900 OF NH-353J | 2021-02-01 | 1166.96 | 1251 | 2023-10-01 | 2024-04-01 | 7.202% | 6.1
64 | RAILWAYS | PUNE-MIRAJ-LONDA (467 KM) | 2015-02-01 | 3627.47 | 6463.49 | 2024-03-01 | 2024-12-01 | 78.18% | 9.1667
65 | ROAD TRANSPORT AND HIGHWAYS | SIX LANING OF CHAKERI TO ALLAHABAD SECTION OF NH-2 FROM KM 483.687 TO KM 628.753 (DESIGN LENGTH – 14 | 2017-11-01 | 2159 | 2262 | 2021-07-01 | 2023-12-01 | 4.771% | 29.4333
66 | URBAN DEVELOPMENT | MUMBAI METRO LINE 3 (COLABA-BANDRA-SEEPZ) | 2013-07-01 | 23136 | 37276 | 2020-03-01 | 2023-12-01 | 61.12% | 45.6667
67 | RAILWAYS | NEW BONGAIGAON-RANGIA-KAMAKGHYA DOUBLING | 2013-04-01 | 1798 | 2047.51 | 2019-03-01 | 2024-01-01 | 13.88% | 58.9
68 | RAILWAYS | SHAHGANJ-BHATNI-PHEPHNA-INDARA, MAU- SHAHGANJ (EXCL. MAU-INDARA) PATCH DOUBLING. | 2016-04-01 | 1177.96 | 1777.39 | 2019-12-01 | 2024-03-01 | 50.89% | 51.7333
69 | PETROLEUM | DURGAPUR-HALDIA PIPELINE PROJECT | 2017-03-01 | 1740 | 2433.15 | 2020-12-01 | 2024-06-01 | 39.84% | 42.6
70 | RAILWAYS | KHARSIA DHARAMJAIGARH WITH SPUR LINE EAST CORRIDOR-PHASE I | 2013-04-01 | 3055 | 3438.39 | 2018-09-01 | 2023-12-01 | 12.55% | 63.9
71 | RAILWAYS | BONGAIGAON-GOALPARA-GUWAHATI (176 KM) | 2015-04-01 | 2232.32 | 4059.65 | 2022-03-01 | 2026-03-01 | 81.86% | 48.7
72 | URBAN DEVELOPMENT | PUNE METRO RAIL PROJECT (PHASE 1) | 2016-12-01 | 11420 | 13656.22 | 2021-11-01 | 2024-03-01 | 19.58% | 28.3667
73 | POWER | NORTH EASTERN REGION POWER SYSTEM IMPROVEMENT PROJECT (NERPSIP) FOR SIX (6) STATES | 2014-12-01 | 5111.33 | 6700 | 2018-12-01 | 2024-12-01 | 31.08% | 73.0667
74 | ROAD TRANSPORT AND HIGHWAYS | 8L OF DWARKA EXPRESSWAY PKG-II (RUB NEAR DWARKA SECTOR 21-DL/HR BORDER) FROM 5.300 KM.TO 9.500 KM. O | 2018-01-01 | 2067.67 | 2160 | 2021-10-01 | 2024-04-01 | 4.465% | 30.4333
75 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF VARANASI GORAKHPUR SECTION OF NH-29 FROM 148.00 208.300 KM [PACKAGE-IV] | 2016-03-01 | 1587.49 | 3063.99 | 2019-04-01 | 2024-03-01 | 93.01% | 59.8667
76 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF GAYA-HISUA-RAJGIRI-NALANDA- BIHARSHARIF SECTION (KM0.00 TO 92.935) ON NH- 82 IN BIHAR | 2014-01-01 | 1408.85 | 2138.16 | 2016-10-01 | 2024-02-01 | 51.77% | 89.3
77 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF POONDIYANKUPPAM (KM.67/000) TO SATTANATHAPOURAM (KM.123/800) SECTION OF NH-45A ON HAM | 2018-03-01 | 2120.4 | 2565.63 | 2022-01-01 | 2024-01-01 | 21% | 24.3333
78 | PETROLEUM | ENNORE THIRUVALLUR BENGALURU PUDUCHERRY NAGAPATTINAM MADURAITUTICORIN GAS PIPELINE | 2016-05-01 | 4497 | 6025 | 2018-12-01 | 2024-03-01 | 33.98% | 63.9
79 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF SULTANPUR TO VARANASI (PKG- I) | 2016-01-01 | 1027.53 | 2628.31 | 2018-06-01 | 2023-12-01 | 155.8% | 66.9667
80 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE EXPRESSWAY FROM KM 190.000 TO KM 217.500 GANDEVA TO ENA SECTION OF VADODA | 2020-07-01 | 1710.3 | 1927 | 2023-08-01 | 2024-06-01 | 12.67% | 10.1667
81 | ROAD TRANSPORT AND HIGHWAYS | 4L OF AUSA-CHAKUR SECTION FROM KM 55.835 TO KM 114.345 OF NH-361 | 2018-03-01 | 1169.04 | 1693.95 | 2021-03-01 | 2023-12-01 | 44.9% | 33.5
82 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF THALSERRY -MAHE BYPASS | 2017-09-01 | 1124.11 | 1503.86 | 2020-05-01 | 2024-01-01 | 33.78% | 44.6667
83 | PETROLEUM | SETTING UP 500KTPA PROPANE DEHYDROGENATION INTEGRATED WITH POLYPROPYLENE UNIT ALONG WITH OFFSITE | 2019-05-01 | 8797 | 11256 | 2025-04-01 | 2025-10-01 | 27.95% | 6.1
84 | RAILWAYS | EAST WEST METRO CORRIDOR KOLKATA | 2009-02-01 | 4874.58 | 10442.41 | 2016-09-01 | 2024-06-01 | 114.2% | 94.3333
85 | RAILWAYS | ROSA-SITAPUR CANTT-BURHWAL DOUBLING | 2015-03-01 | 1295 | 2560 | 2022-03-01 | 2024-02-01 | 97.68% | 23.4
86 | RAILWAYS | SEVOK RANGPO, NEFR | 2008-04-01 | 1339 | 7876.92 | 2015-12-01 | 2023-12-01 | 488.3% | 97.4
87 | POWER | BARH STPP(3X660MW) NTPC | 2005-02-01 | 8692 | 21312.11 | 2011-10-01 | 2024-08-01 | 145.2% | 156.2667
88 | PETROLEUM | VISAKH REFINERY MODERNISATION PROJECT | 2016-07-01 | 20928 | 26264 | 2020-07-01 | 2024-04-01 | 25.5% | 45.6667
89 | PETROLEUM | NUMALIGARH REFINERY EXPANSION PROJECT 6 MMTPA REFINARY | 2019-01-01 | 12366 | 18968 | 2024-10-01 | 2025-07-01 | 53.39% | 9.1
90 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM BARANAGAR TO BARRACKPORE AND DAKSHINESHWAR (MTP) | 2010-04-01 | 2298 | 2733.86 | 2014-03-01 | 2025-12-01 | 18.97% | 143.1
91 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF EIGHT LANE ACCESS CONTROLLED EXPRESSWAY FROM KM 217.500 TO KM 254.430 OF VADODARA | 2020-07-01 | 2271 | 3916 | 2023-12-01 | 2024-06-01 | 72.44% | 6.1
92 | ROAD TRANSPORT AND HIGHWAYS | ALIGARH-KANPUR SECTION PACKAGEV FROM MITRASEN-KANPUR | 2019-10-01 | 2325 | 3601.57 | 2023-09-01 | 2023-10-01 | 54.91% | 1
93 | PETROLEUM | MUMBAI HIGH NORTH REDEVELOPMENT PHASE-IV | 2019-04-01 | 3228 | 3976.67 | 2022-03-01 | 2024-06-01 | 23.19% | 27.4333
94 | RAILWAYS | RATLAM-MHOW-KHANDWA-AKOLA (GC) | 2008-04-01 | 3503 | 6203.51 | 2022-03-01 | 2026-03-01 | 77.09% | 48.7
95 | ROAD TRANSPORT AND HIGHWAYS | LUCKNOW RING ROAD PKG-1 (SULTANPUR ROAD TO BEHTA ROAD) [BYPASS CONNECTING NH-56 AT KM. 17.40 | 2018-01-01 | 1916.38 | 2078 | 2023-02-01 | 2024-01-01 | 8.434% | 11.1333
96 | ROAD TRANSPORT AND HIGHWAYS | 6-LANING OF KOZHIKODE BYPASS (CALICUT BYPASS) (I.E. VENGALAM JN. TO RAMANATTUKARA JN.) | 2018-02-01 | 1424 | 1862.77 | 2023-02-01 | 2024-12-01 | 30.81% | 22.3
97 | ROAD TRANSPORT AND HIGHWAYS | HOSPET-BELLARY-KARNATAKA AP BORDER | 2016-08-01 | 1167 | 1224.01 | 2019-03-01 | 2025-05-01 | 4.885% | 75.1
98 | RAILWAYS | KAZIPET-VIJAYAWADA 3RD LINE WITH ELECTRIFICATION | 2012-04-01 | 1856 | 1952.68 | 2023-03-01 | 2025-03-01 | 5.209% | 24.3667
99 | RAILWAYS | NEW WORK FOR CONSTRUCTION OF METRO RAILWAY FROM NSCB AIRPORT TO NEW GARIA VIA RAJARHAT (MTP) | 2010-04-01 | 3951 | 8964.35 | 2016-03-01 | 2026-03-01 | 126.9% | 121.7333
100 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BETTADAHALLI TO SRIRAMPURA SECTION FROM KM. 166+100 (DESIGN KM. 170+415) TO KM. 217+0 | 2021-10-01 | 1331 | 2082.98 | 2023-10-01 | 2024-10-01 | 56.5% | 12.2
101 |  | 4-LANING OF LOHA - WARANGA SECTION OF NH- 361 FROM KM. 187.800 TO KM. 244.369 (DESIGN LENGTH 56.569 K | 2018-03-01 | 1005 | 1073.1 | 2021-03-01 | 2024-03-01 | 6.776% | 36.5333
102 | RAILWAYS | CHOTTAUDEPUR-DHAR(NL) | 2007-04-01 | 1347 | 1793.63 | 2022-03-01 | 2026-12-01 | 33.16% | 57.8667
103 | RAILWAYS | TARAKESWAR - BISHNUPUR NEW BG LINE (NL) | 2000-04-01 | 1188 | 1619.51 | 2019-03-01 | 2024-03-01 | 36.32% | 60.9
104 | RAILWAYS | HOSPET-HUBLI-LONDA-VASCODAGAMA DL | 2010-04-01 | 2127 | 3692.6 | 2023-03-01 | 2024-03-01 | 73.61% | 12.2
105 | RAILWAYS | ANUPPUR-KATNI | 2015-04-01 | 1370 | 1680 | 2021-12-01 | 2024-12-01 | 22.63% | 36.5333
106 | RAILWAYS | JHARSUGUDA-BILASPUR 4TH LINE | 2015-04-01 | 1973 | 2135.34 | 2021-03-01 | 2024-10-01 | 8.228% | 43.6667
107 | URBAN DEVELOPMENT | PATNA METRO RAIL CORPORATION LIMITED | 2019-02-01 | 13365 | 13925.5 | 2024-06-01 | 2024-09-01 | 4.194% | 3.0667
108 | RAILWAYS | KAZIPET-BALHRSHA | 2015-04-01 | 2063 | 2909 | 2021-03-01 | 2025-01-01 | 41.01% | 46.7333
109 | RAILWAYS | NEW LINE FROM DIMAPUR TO ZUBZA(KOHIMA) NATIONAL PROJECT (NEFR) | 2006-04-01 | 2326 | 6663 | 2015-03-01 | 2026-03-01 | 186.5% | 133.9333
110 | RAILWAYS | RISHIKESH - KARNAPRAYAG NEW LINE | 2011-04-01 | 16216 | 24659 | 2024-12-01 | 2025-03-01 | 52.07% | 3
111 | ROAD TRANSPORT AND HIGHWAYS | DWARKA EXPRESSWAY FROM KM -0.600 TO KM 5.300 - PKG-I (SHIVMURTI CHOWK-RUB NEAR DWARKA SECTOR 21) | 2018-03-01 | 2507 | 3030.73 | 2022-09-01 | 2024-06-01 | 20.89% | 21.3
112 | RAILWAYS | DAHOD-INDORE VIA SARDARPUR, JHABUA AND DHAR (NL) | 2007-04-01 | 1640 | 2690.8 | 2022-03-01 | 2026-03-01 | 64.07% | 48.7
113 | ROAD TRANSPORT AND HIGHWAYS | 6-LANING OF VIJAYAWADA BYPASS FROM CHINNA AVUTUPALLI (DESIGN CH.0+000) TO GOLLAPUDI | 2019-11-01 | 1226 | 1581.24 | 2021-02-01 | 2024-03-01 | 28.98% | 37.4667
114 | ROAD TRANSPORT AND HIGHWAYS | CHAKUR LOHA SECTION OF NH-361 FROM KM 114.600 TO KM 187.80 | 2018-03-01 | 1241 | 2122.64 | 2023-03-01 | 2024-01-01 | 71.04% | 10.2
115 | RAILWAYS | MANOHARABAD-KOTHPALL NEW LINE(SCR) | 2006-04-01 | 1160 | 3014 | 2010-03-01 | 2025-03-01 | 159.8% | 182.6333
116 | ROAD TRANSPORT AND HIGHWAYS | SIX LANNING FROM KM. 401.200 TO 494.410 OF NH-8 ON HYBRID ANNUITY MODE UNDER NHDP-V(PKG VI)REG. | 2017-01-01 | 1251 | 1361 | 2020-12-01 | 2024-03-01 | 8.793% | 39.5333
117 | ROAD TRANSPORT AND HIGHWAYS | FOUR LANING OF BAKHTIYARPUR - MOKAMA SECTION OF NH-31 | 2015-12-01 | 1167 | 1182.94 | 2019-12-01 | 2023-12-01 | 1.366% | 48.7
118 | POWER | VISHNUGAD PIPALKOTI HYDRO ELECTRIC PROJECT | 2008-08-01 | 2491 | 3860.35 | 2013-06-01 | 2026-06-01 | 54.97% | 158.2667
119 | ROAD TRANSPORT AND HIGHWAYS | CONSTRUCTION OF 4-LANE GREEN FIELD DELHI- AMRITSAR-KATRA EXPRESSWAY (NE-05) FROM JUSSUR KHERI ON KMP | 2020-11-01 | 1690 | 2010.17 | 2023-12-01 | 2024-03-01 | 18.94% | 3.0333
120 | ROAD TRANSPORT AND HIGHWAYS | 4-LANNING OF HARIDWAR-NAGINA SECTION OF NH 74 FROM (KM 204.300 OF NH 58) TO KM 73.00 | 2016-03-01 | 1408 | 1659.12 | 2020-07-01 | 2024-05-01 | 17.84% | 46.6667